Response to WHO RFP 2026_PHL-14_NCD-07_305898

Financial Proposal — Annex E

Technical Assistance for the Development and Implementation of Standardized Barangay Health Worker Training for Integrated NCD Care

FINANCIAL PROPOSAL — submit as its own email/envelope, subject “FINANCIAL PROPOSAL,” with Annex H if applicable. Currency: PHP.

Proposer: Bureau of Local Health Systems Development (BLHSD) delivery team, Department of Health, Republic of the Philippines

Counterpart: WHO Philippines / HSS / NCD Management

Status: DRAFT for internal BLHSD review. All unit rates below are illustrative placeholders, marked [RATE TBC], pending BLHSD's own costing against market rates — to be confirmed before submission.

How the ₱1,500,000 BLHSD line is treated in this budget It is priced as its own labeled block (Section B.2), not distributed invisibly across other lines, and the Grand Total already includes it — it is not an amount requested in addition to the Grand Total. If BLHSD needs to adjust overall pricing before submission, this block's ₱1,500,000 should be held constant and the other Output lines adjusted, so the inclusion stays exactly what was represented to WHO in the Technical Proposal.

# B.1  Cost by Output

## Output 1 — Inception, Framework & Implementation Design

| ITEM | COST (₱) |
| --- | --- |
| Project Manager costs | 150,000 [RATE TBC] |
| Team members costs (curriculum designer, NCD/clinical advisor) | 300,000 [RATE TBC] |
| Other technical costs (materials review, workplan tools) | 50,000 [RATE TBC] |
| Other costs | 50,000 [RATE TBC] |
| Output 1 Costs | 550,000 |

## Output 2 — Standardized Training Package Development

| ITEM | COST (₱) |
| --- | --- |
| Project Manager costs | 250,000 [RATE TBC] |
| Team members costs (instructional designers ×2, clinical writer, video producer) | 1,800,000 [RATE TBC] |
| Bilingual video production, 6 modules (scripting, shoot, edit, graphics) | 1,150,000 [RATE TBC] |
| Other technical costs (authoring/production software) | 150,000 [RATE TBC] |
| Other costs | 100,000 [RATE TBC] |
| Output 2 Costs | 3,450,000 |

## Output 3 — Validation & Finalization

| ITEM | COST (₱) |
| --- | --- |
| Project Manager costs | 150,000 [RATE TBC] |
| Team members costs (technical writers, reviewers' honoraria) | 400,000 [RATE TBC] |
| Workshop/venue/logistics (technical review meetings, validation workshops) | 300,000 [RATE TBC] |
| Other costs | 50,000 [RATE TBC] |
| Output 3 Costs | 900,000 |

## Output 4 — District-Level Implementation & Competency Validation

| ITEM | COST (₱) |
| --- | --- |
| Project Manager costs | 200,000 [RATE TBC] |
| Team members costs (trainers/facilitators, qualified assessors) | 900,000 [RATE TBC] |
| Training logistics (venues, materials reproduction, in-region travel per Sections 5.4/5.7) | 700,000 [RATE TBC] |
| Other costs (assessment-tool printing/reproduction) | 100,000 [RATE TBC] |
| Output 4 Costs | 1,900,000 |

## Output 5 — Final Reporting & Recommendations for Scale-Up

| ITEM | COST (₱) |
| --- | --- |
| Project Manager costs | 150,000 [RATE TBC] |
| Team members costs (M&E/reporting specialist) | 300,000 [RATE TBC] |
| Other costs (final package production/formatting) | 50,000 [RATE TBC] |
| Output 5 Costs | 500,000 |

Subtotal, Outputs 1–5: ₱7,300,000

# B.2  Highlighted Inclusion — BLHSD Institutional Capacity Investment (5 months)

Cross-referenced to the Technical Proposal, Section A.3.3. Covers the full 5-month contract duration — the same duration as Output 1–5 delivery above, per TOR Section 5.5.

| ITEM | COST (₱) |
| --- | --- |
| 3 BLHSD-embedded staff (Digital Platform / Content Development Officers), Equity in Health and Special Concerns Section, 5 months full-time | 1,125,000 [RATE TBC] |
| AI / productivity subscription for BLHSD office, 5 months | 375,000 [RATE TBC] |
| BLHSD Institutional Capacity Investment — Total | 1,500,000 |

# B.3  Contingency and Grand Total

| ITEM | COST (₱) |
| --- | --- |
| Subtotal, Outputs 1–5 (Section B.1) | 7,300,000 |
| BLHSD Institutional Capacity Investment (Section B.2) | 1,500,000 |
| Contingency — 5% of Outputs 1–5 | 365,000 [RATE TBC] |
| GRAND TOTAL COST OF THE PROPOSAL | 9,165,000 |

≈ US$158,000 at ₱58/US$ (reference rate only; RFP Article 13 requires conversion at the UN Operational Rate of Exchange on the closing date for bid submission).

The BLHSD Institutional Capacity Investment (₱1,500,000) is fully contained within this Grand Total — it is 16.4% of the total proposed price, not an amount on top of it.

The enclosed Proposal is valid for 60 days from the deadline for proposal submission, per RFP Section 3 (Article 14).

## Agreed and accepted

| Field | Entry |
| --- | --- |
| Company Name | Bureau of Local Health Systems Development (BLHSD), Department of Health |
| Mailing Address | [TO CONFIRM] |
| Name and Title of duly authorized representative | [TO CONFIRM] |
| Signature |  |
| Date | [TO CONFIRM] |